## Sheet1
Risk ID | Risk Category | Risk Description | Impact Score (1-5) | Likelihood % | Risk Rating | Risk Response | Contingency Plan | Risk Category | Definition
Project Risks | [7 empty] | Project Execution | Risks affecting the development of the project e.g. systems, technologies, code etc.
R1 | Project Execution | Project too complicated/difficult to complete | 5 | 25% | 1.25 | Risk Avoidance | Thorough technical analysis and prototyping | Personnel | Risks affecting the human aspect of the project
R2 | Project Execution | Run time performance issues | 3 | 25% | 0.75 | Mitigation | Code optimization to improve performance | Schedule | Risks that could affect the schedule and cause time delays during development
R3 | Project Execution | MVC compatibility issues | 3 | 40% | 1.2 | Mitigation | Carry out adequate testing during each development stage to check each component is compatable with one antoher | Compliance | Risks associated with failure to meet regulatory standards
R4 | Project Execution | Project not within scope | 3 | 30% | 0.9 | Risk Avoidance | Ensure project is still within scope during supervisor meetings | Loss | Risks related to the loss of work, hardware or data
R5 | Project Execution | Changes to technologies during development | 2 | 35% | 0.7 | Mitigation
Personnel Risks | [7 empty] | Risk Response | Definition
R6 | Personnel | Insufficient knowledge to complete system requirements | 4 | 25% | 1 | Risk Avoidance | Ensure enough research is carried out before development begins (mostly during sprint zero) | Risk Avoidance | Eliminating the risk before it occurs
R7 | Personnel | Unexpected illness or personal issues | 2 | 30% | 0.6 | Mitigation | Alter current schedule and pushback tasks into next sprints if required | Mitigation | Reducing the damage caused when this risk occurs
Schedule Risks | [7 empty] | Acceptance | Accepting the risk
R8 | Schedule | Unexpected server downtime/maintenance | 1 | 75% | 0.75 | Acceptance | None
R9 | Schedule | Time constraints due to other commitments | 3 | 30% | 0.9 | Mitigation | Improved planning and alteration to current schedule | Probability Level | Range
R10 | Schedule | Issues related to the COVID-19 Pandemic | 2 | 60% | 1.2 | Mitigation | [Dependant on restrictions and changes] | High | Greater than 50%
Compliance Risks | [7 empty] | Significant | 30-50% chance
R11 | Compliance | Potential copyright infringement with similar products | 1 | 25% | 0.25 | Acceptance | As this is project is for educational purposes this risk can be accepted but will still need to be taken into consideration | Moderate | 10-29% chance
R12 | Compliance | Unintentional regulatory noncompliance’s | 1 | 10% | 0.1 | Acceptance | Same as above | Low | Less than 10% chance
Loss Risks
R13 | Loss | Accidental loss of work | 3 | 20% | 0.6 | Mitigation | Create multiple backups to keep loss to a minimum
R14 | Loss | Theft/Fraud | 4 | 10% | 0.4 | Acceptance | None